# SmartPark by $oftware ¢orp - Smart Parking Platform Project

# v 4.0

Bookmarks:

SRS

WBS

GanttChart

JiraScrumBoard

RiskCategories

RiskRegister

CommunicationPlan

Existing Software Landscape:

Most used parking platforms in Houston: ParkHouston by ParkMobile, SpotHero, ParkWhiz

Shared core features:

- Search for participating parking garages on map via GPS

- GPS integration within app with directional navigation to garage from current location

- Reserve spot ahead of time or on the spot in parking garages or street lots

- Extended parking time up to maximum limit via app

- Electronic receipt system via QR code or license plate recognition

- Payment in app via credit/debit card, Apple/Google Pay, PayPal

- Register several license plates/save several cars to single account

- Receive notifications for parking expiration

- Track purchase history

Unique Features:

- ParkHouston by ParkMobile:

  - Mobile and web parking service for city-managed street and garage parking in Houston

  - Most common for on-the-spot street parking in municipal areas

  - Feature: Find car with directions back to parking spot

- SpotHero:

  - Mobile and web parking service for private street and garage parking or event parking across the U.S.

  - Large number of participating garages in many cities

  - Most common for garage parking with reservations

- ParkWhiz:

  - Mobile and web parking service for private street and garage parking or event parking across the U.S.

  - Most common for reserving event parking, such as concerts, sports games, venues

  - Offers discounts/coupons

What SmartPark Houston will offer:

The SmartPark Houston by $oftware ¢orp application will stand out in its partnership with all garage operators in the Houston downtown area, so that drivers can have access to search all parking garages in a single app; no need to download several apps to find the best garage option. Also, SmartPark will have various modes of access, such as app, site, QR code, and text-to-pay to better serve the preferences of all drivers. SmartPark will establish a loyalty/benefits program for frequent travelers to save up rewards, earn coupons and discounts with each reservation.

# Software Requirements Specification (SRS)

Project: SmartPark Houston – a Smart Parking Platform by $oftware ¢orp

Version: 1.0

Date: September 10, 2026

- Introduction:

$oftware ¢orp has recognized the demand for better parking management in the Houston area due to a large population of commuting residents and an increase in tourism. As a leader in software development, we are determined to present a modern solution to optimize garage parking services for both users and operators.

- Purpose

The goal of SmartPark Houston is to optimize parking management for both drivers and garage operators through software that provides information for parking availability, reservation, navigation, and payment all in one platform. This document defines the requirements for SmartPark.

- Scope

- Create a website and mobile application that integrates with partnered private garages in Houston

- Allow vehicle owners/drivers to reserve a parking space in real-time or in advance, use navigation, and complete payments within the app

- Allow garage operators to monitor occupancy and manage pricing

- Semester timeline - to be completed within 4 months

Out of scope:

- Extended timeline

- Integration with parking garages outside of Houston downtown area

- Integration with “buy now, pay later” platforms, such as Klarna, Afterpay

- Overall Description:

- Users: Drivers/vehicle owners, garage operators (admin)

- System Environment: Website and mobile application

- Constraints:

  - Must require vehicle registration via license plate, must be compatible with partnered parking garages, must show live/real-time information, must be compatible with GPS, must integrate with payment platforms.

  - Fixed timeline – semester (4 months)

  - Unlimited budget

  - Dependence on third-party services

  - Compliance with security, privacy regulations, city laws

- Assumptions: Developers/development team is available to work on project, studio has technology equipment needed to develop software, parking garages have capabilities to utilize mobile parking services

- Use Case Examples:

- Title: Application Installation

Actor: User

Goal: Install SmartPark app on iPhone

Precondition: User owns iPhone device, has AppStore

Steps:

- User opens AppStore application

- User searches for “SmartPark”

- User selects “Get” to install app

- User selects “Open” to open app on home screen

- Title: Application Installation

Actor: User

Goal: Install SmartPark app on Android

Precondition: User own Android device, has Google Play Store

Steps:

- User opens Google Play Store application

- User searches for “SmartPark”

- User selects “Install” to install app

- User selects “Open” to open app on home screen

- Title: Registration and Authentication for drivers

Actor: User (vehicle owner/driver)

Goal: Create user account

Steps:

- User selects “Driver Sign Up”

- User inputs username/email, password

- User adds vehicle license plate number and car details

- User saves login information

- Title: Registration and Authentication for operators

Actor: User (parking garage operator)

Goal: Create admin account

Steps:

- User selects “Operator Sign Up”

- User inputs username/email, password

- User adds parking garage location, documentation

- User saves login information

- Title: Adding Payment Preference

Actor: User (vehicle owner/driver)

Goal: Save payment information for Credit/Debit card

Precondition: User is logged into app

Steps:

- User selects “Select Payment Option”

- User selects “Credit/Debit card”

- User selects “Visa”, “Mastercard”, or “American Express”

- User inputs card number, expiration, security code

- User selects “Save”

Postcondition: User can pay automatically upon checkout with saved card

- Title: Paying with Digital Wallet on iPhone

Actor: User (vehicle owner/driver)

Goal: Pay for parking using digital wallet

Precondition: User is logged into app and is ready to pay

Steps:

- User selects “Apple Pay”

- User reviews parking reservation details

- User double clicks side button and enters face ID to authenticate payment

- Screen shows checkmark to confirm payment was successful

- User receives message of the Apple Pay payment

Postconditions: User receives text or email receipt from SmartPark with reservation details and payment confirmation

- Title: Paying with Digital Wallet on Android

Actor: User (vehicle owner/driver)

Goal: Pay for parking using digital wallet

Precondition: User is logged into app and is ready to pay. User has set up Google pay by connecting it with credit/debit card

Steps:

- User selects “Google Pay”

- User reviews credit/debit card information

- User reviews parking reservation details

- User authenticates payment with face ID or passcode

- Screen shows checkmark to confirm payment was successful

Postconditions: User receives text or email receipt from SmartPark with reservation details and payment confirmation

- Title: Paying with Text-to-Pay

Actor: User (vehicle owner/driver)

Goal: Pay for parking via text-to-pay feature for on-the-spot parking

Preconditions: User has located a Text-to-Pay sign with text code information. User does not have an account with SmartPark.

Steps:

- User texts the number written on the Text-to-Pay sign from a mobile device

- User receives a link

- User is directed to the SmartPark website after clicking on the link

- User confirms parking garage name and location

- User is prompted to enter name, contact information, vehicle details/license plate number.

- User saves details, selects “Continue”

- User is directed to the payment page

- User chooses desired payment option

- User confirms card details

- User authenticates payment

- User receives confirmation of successful payment

Postcondition: User receives text or email receipt from SmartPark with reservation details and payment confirmation

- Title: Search for available parking spots

Actor: User (vehicle owner/driver)

Goal: See live availability of parking spots in garage

Precondition: User is logged into app

Steps:

- User selects map feature showing Houston downtown area

- User sees all partnered garages indicated by dots

- User selects one available parking garage indicated by a green dot

- User sees the name of the selected garage and the number of available spaces

- Title: Parking reservation in advance

Actor: User (vehicle owner/driver)

Goal: Reserve parking space in garage ahead of time

Precondition: User is logged into app and has selected desired garage

Steps:

- User confirms selected garage has space availability

- User selects “Continue”

- User enters date and time for reservation

- User selects “Continue”

- User reviews confirmation page with garage information, vehicle details, date of reservation, duration of reservation, and contact information

- User selects “Checkout”

Postcondition: User pays for parking space and receives receipt for reservation

- Title: Extending parking reservation time

Actor: User (vehicle owner/driver)

Goal: Extend time for parking space

Precondition: User is logged into app, has paid for space, and is actively parked

Steps:

- User selects “Extend reservation” control

- User is prompted to enter time in minutes and hours to be added to the current reservation window

- User sees the cost of the additional time

- User selects “Confirm”

- User is prompted to enter payment information or select the same method as was used for the original reservation

- User confirms payment with Face ID or passcode authentication

- User receives confirmation page showing successful payment

- User receives text or email receipt showing new expiration time for parking space

- Title: Navigational Services

Actor: User (vehicle owner/driver)

Goal: Direct user to garage location in app

Precondition: User is logged into app

Steps:

- User selects “Map”

- User searches location and selects desired parking garage

- User selects “Directions”

- User is prompted to enter their location/address as the “From”

- User selects “Go”

- User receives visual and verbal navigational instructions within the SmartPark app

- User selects “Arrived” once arrived and parked at destination

- Title: Car Location Services

Actor: User (vehicle owner/driver)

Goal: Locate car in garage structure

Precondition: User is logged into app and is returning to garage at the end of their reservation. User has location services on for SmartPark app

Steps:

- User selects “Active Parking”

- User confirms their current parking space reservation

- User selects “Locate Car”

- User is redirected to the map feature

- User receives directional instructions indicated by an arrow along mapped streets

- User follows arrow to parking garage structure and enters

- User is redirected to the garage layout map

- User receives instructions with floor number, zone letter, and space number of their parked car

- User selects “Car Found” to end directions

- Title: Payment tracking

Actor: Admin (Parking garage operator)

Goal: Show earning details

Precondition: User is logged into app

Steps:

- User selects “Earnings Report” on dashboard

- User enters desired date

- User receives a page showing the total earnings for the selected day

- User selects “Save Report”

- Title: Occupancy reporting

Actor: Admin (Parking garage operator)

Goal: Report number of reserved parking spaces in garage

Precondition: User is logged into app

Steps:

- User selects “Occupancy Report” on dashboard

- User enters desired date

- User receives a page showing the total number of garage reservations/occupants on a selected day

- User selects “Save Report”

## Work Breakdown Structure (WBS)

- Smart Parking Platform

  - Research

    - Existing Software Landscape

  - Requirements

    - SRS

      - Use Cases

  - Authentication

    - Registration

      - Username and password

      - Vehicle/license plate

      - Security verification

    - Login

      - Autocomplete

  - User Setup

    - Dashboard

      - Map integration

    - Profile

      - Account management

    - Session Management

      - New reservation

      - Past reservations

  - Operator Setup

    - Dashboard

      - Analytics

    - Profile

      - Locations

      - Pricing

      - Hours

  - Garage Monitoring

    - Map search

      - GPS integration

      - Search filters

    - Select garage

    - Spot availability

    - Booking reservation

  - Payment

    - Payment gateway

      - PayPal integration

      - Apple Pay integration

      - Google Pay integration

      - Credit/Debit integration

  - Reporting

    - Garage occupancy

    - Financial revenue

    - Security

### Gantt Chart

Story points:

Timeline:

Chart:

Story points (SP) with  timeline estimation:

- Existing Software Landscape – 1 SP (~48-72 hrs)

- Use Cases – 1SP (~1-2 wks)

- Login – 2 SP (~24-48 hrs)

- Autocomplete – 1 SP (~24 hrs)

- Username and password – 2 SP (~24-48 hrs)

- Vehicle/license plate – 3 SP (~24-48 hrs)

- Security verification – 5 SP (~72-96 hrs)

- User/Operator Dashboard – 5 SP (~72-96 hrs)

- Map integration – 8 SP (1-2 wks)

- Profile management – 5 SP (~24-48 hrs)

- New reservation management – 5 SP (~24-48 hrs)

- Past reservations management – 5 SP (~24-48 hrs)

- Operator Analytics – 3 SP (~48-72 hrs)

- Operator Locations – 3 SP (~24-48 hrs)

- Operator Pricing - 3 SP (~24-48 hrs)

- Operator Hours – 2 SP (~24-48 hrs)

- Garage map search – 5 SP (~48-72 hrs)

- GPS integration – 8 SP (~1-2 wks)

- Search filters – 3 SP (~24-48 hrs)

- Select garage – 2 SP (~24-48 hrs)

- Spot availability – 5 SP (~48-72 hrs)

- Booking reservation – 5 SP (~48-72 hrs)

- Payment gateway – 8 SP (1-2 wks)

- Garage occupancy report – 5 SP (~72-92 hrs)

- Financial revenue report – 5 SP (~72-92 hrs)

- Security report – 5 SP (~72-92 hrs)

## Jira Scrum Board

## Risk Categories

Technical risks:

- App may not work without proper cellular connection

- Payment API failure

- License plate recognition technology not working

- Misrepresented spot availability due to malfunctioning sensors

Schedule risks:

- App launch delay

- Underestimated timeline

- City approval challenges or delays

- Third-party services approval delays

Financial risks:

- Scope creep

- Third-party service costs

- App temporarily stops working/outage

- Going over budget

People risks:

- Team member quitting

- Team member getting sick

- Team member fails to fulfill assigned task by deadline

- Team member incorrectly completes assigned task

## Risk Register

Risk ID: TR01

Description: Payment API failure

Category: Technical risk

Probability: Medium

Impact: High

Owner: API developers

Response Strategy: Immediate action from API engineers to fix software

Status/Notes: Not started

Risk ID TR02

Description: License plate recognition technology not working

Probability: High

Category: Technical risk

Impact: High

Owner: Garage technician, software engineer

Response Strategy: Immediate action by on location troubleshooting and/or fixing software. Mitigate risk by proper upkeep of hardware and regular software updates.

Status/Notes: Not started

Risk ID SR03

Description: Underestimated timeline

Probability: High

Category: Schedule risk

Impact: High

Owner: Project manager

Response Strategy: Reevaluate goals and deliverables; make timeline adjustments. Mitigate by allowing flexibility in time estimates.

Status/Notes: High priority

Risk ID SR04

Description: City approval delays

Probability: Medium

Category: Schedule risk

Impact: High

Owner: Project manager

Response Strategy: Accept delay, adjust project timeline

Status/Notes: High priority

Risk ID FR05

Description: App temporarily stops working/outage

Probability: Medium

Category: Financial risk

Impact: High

Owner: App developers

Response Strategy: Immediate action from software team. Mitigate risk by running regular tests and updates (during low traffic times)

Status/Notes: High priority

Risk ID FR06

Description: Going over budget

Probability: High

Category: Financial risk

Impact: Medium

Owner: Project manager

Response Strategy: Make plan for budget flexibility. Mitigate by avoiding additional, sudden requests (scope creep)

Status/Notes: Medium priority, not started (due to undisclosed budget limit)

Risk ID PR07

Description: Team member fails to fulfill assigned task by deadline

Probability: Medium

Category: People risk

Impact: Medium

Owner: Software developer

Response Strategy: Mitigate – evaluate skills and capabilities of team members. Reassign tasks.

Status/Notes: Not started

Risk ID PR08

Description: Team member incorrectly completes assigned task

Probability: Medium

Category: People risk

Impact: High

Owner: Software developer

Response Strategy: Transfer task to another developer. Mitigate – evaluate skills and capabilities of team members. Reassign tasks.

Status/Notes: Not started

Risk ID FR09

Description: Third-party service costs

Probability: Medium

Category: Financial risk

Impact: Medium

Owner: Project manager

Response Strategy: Reevaluate budget

Status/Notes: Not started

Risk ID PR10

Description: Team member getting sick

Probability: Medium

Category: People risk

Impact: Low

Owner: Team manager

Response Strategy: Transfer task to another developer

Status/Notes: Low priority

## Communication Plan

Meeting cadence per team:

- Daily: 10-15 min., virtual. Department team of ~5-10 people meet to discuss immediate progress, challenges, and completion of their group’s shared tasks

    - Individual development teams

      - Organized by team lead

  - Reporting methods: daily standups – 3 questions

- Weekly: 20-30 min, virtual or in-person. Project team of ~15-20 people with manager meet to discuss each department team’s progress over weeks, resolving interdepartmental challenges

    - All development teams and management

      - Organized by middle managers

  - Reporting methods: project management tools for visualization of progress (scrum board, gantt chart), technical details/reports

- Monthly: 30-45 min., virtual or in-person. Leadership and stakeholders ~20-30 people meet to discuss project progress, milestones, and review timeline/budget

    - Upper management and stakeholders

      - Organized by executives

  - Reporting methods: metrics analysis, overview summary with focus on main accomplishments or setbacks